# Agile Delivery Plan: Payment Verification & Reconciliation Automation

Timeline, Team, Initial Requirements, and Cost Estimate – 500 Transactions/Day Scenario

Table of Contents

1. Summary of Approach	1

2. Key Assumptions (To Be Validated With Stakeholders)	2

3. Initial Requirements / Sprint 0 (Definition of Ready)	2

4. Team & RACI Structure	3

5. Product Backlog (Epic Level)	4

6. Sprint Plan & Timeline	5

7. Ceremony Cadence	6

8. Definition of Done (Example, to Be Re-Agreed in Sprint 0)	7

9. Phase 2 & Phase 3 Roadmap (High Level)	7

10. Risks to the Timeline	7

11. Cost Estimate – 500 Transactions/Day Scenario	8

Appendix – Additional Assumptions & Clarifying Questions	11

Version: 1.0 (Delivery planning draft, a companion to the earlier Technical Design Document) Methodology: Scrum, 2-week sprints

## 1. Summary of Approach

This project is executed using Scrum (2-week sprints) because its scope touches many interdependent components (OCR, folder automation, matching engine, security) that require a fast feedback loop and the ability to re-prioritize as soon as assumptions (Appendix A in the earlier document) get confirmed or change in the field.

Overall structure:

- Sprint 0 (Discovery/Setup) – 2 weeks, not a feature-development sprint, but ensuring the Definition of Ready is met.

- Sprints 1-6 (MVP Build) – 12 weeks, building the MVP scope from the technical design document (Section 34).

- Sprint 7 (Hardening, UAT, Pilot Go-Live) – 2 weeks.

- Total MVP: ~16 weeks (~4 months) from kickoff to pilot go-live with 1-2 banks.

This is an illustrative estimate based on the team-size assumptions in Section 4 – the real duration may change once Sprint 0 is complete and the backlog is refined with the actual team’s estimates.

## 2. Key Assumptions (To Be Validated With Stakeholders)

The timeline, team, and cost estimates in this document are built on the following assumptions:

- Costing volume basis: 500 transactions/day (~15,000/month) – per the requested scenario, sitting between the “100/day” and “1,000/day” tiers in the earlier scalability analysis (Section 32).

- The core team works onshore in Malaysia, hybrid working model, mostly full-time hires (in-house) – an alternative outsourcing/turnkey vendor scenario is also given as a comparison in Section 11.

- Standard: 1 sprint = 2 weeks = ~9-10 effective working days (after ceremony overhead).

- The company already has a basic cloud subscription (Azure/GCP/AWS) or is willing to set one up – internal procurement/approval is not counted as part of the sprint timeline (it must be completed before Sprint 1, see Section 3).

- The MVP targets the 2-3 highest-volume banks first (per the recommendation in Section 34 of the earlier document), not every bank at once.

- All cost estimates are in Malaysian Ringgit (RM) unless stated otherwise, based on 2026 market benchmark data (Section 11) – not an official vendor quote.

## 3. Initial Requirements / Sprint 0 (Definition of Ready)

Sprint 0 focuses on making sure the team is not blocked the moment Sprint 1 starts. The following checklist must be complete before Sprint 1:

### 3.1 Access & Data

- At least 30-50 real sample receipt images (photo/screenshot, anonymized if needed) from the 2-3 banks targeted for the MVP.

- At least 2-3 real bank XLSX files (dummy/anonymized data) for each target bank, to build the column mapping config (Technical Design Document Section 13).

- Written confirmation from the finance/teller team on the meaning of fields 3 and 8 in the teller string format (see Appendix A/B of the earlier document) – a critical blocker for Epic A, must be resolved in Sprint 0.

- Access to the WhatsApp Business API (sandbox/test number) for the bot already in operation.

- Sandbox/trial credentials for at least 1 OCR provider (Azure/Google/AWS) for an initial proof of concept.

### 3.2 Environment & Tooling

- A cloud subscription (dev + staging) is available, with a resource group/project separate from existing production.

- A code repository + a basic CI/CD pipeline (build, lint, test) is already working.

- A secure folder for bank XLSX files (Option 1, Section 20 of the earlier document) has been set up by IT with the correct permissions.

- A Microsoft Teams account/finance notification channel has been created (if migrating away from the WA group is agreed).

### 3.3 Governance & People

- A business-side Product Owner (finance ops) has been appointed and available for at least 50% of their time throughout the project.

- The security team has had an initial briefing on the proposed architecture (so the approvals in Sections 20/21 don’t become a surprise blocker in Sprint 6/7).

- Definition of Ready and Definition of Done (Section 8) have been agreed with the team.

Sprint 0 output: a brief project charter, an initial backlog refined with rough estimates (Section 5), the final technical architecture approved, and every item on the checklist above checked off.

## 4. Team & RACI Structure

### 4.1 Proposed Team Composition

| Role | Allocation | Main Responsibility |
| --- | --- | --- |
| Product Owner (PO) | 50% | Backlog prioritization, bridge to finance/the business, accepts/rejects sprint output |
| Scrum Master (SM) | 20% (combined with the PO/Tech Lead for a team this small) | Facilitates ceremonies, removes blockers |
| Solution Architect (SA) | 50% | Architecture decisions, reviews the design of each epic, coordinates with security/IT |
| Backend Engineer x2 (BE) | 100% each | API, database, matching engine, integration |
| Data Engineer (DE) | 75% | Data schema, XLSX normalization, bank data pipeline |
| OCR/Document AI Engineer | 75% | Classification, extraction, confidence scoring |
| Automation/Integration Engineer | 100% | Folder watcher, notifications (Teams/WA), external integration |
| Security Engineer | 30% (can be a part-time consultant) | RBAC, secrets management, security review each sprint |
| QA Engineer | 50% | Test plan, regression, UAT coordination |
| Finance SME | A stakeholder, not part of the delivery team | Requirement validation, UAT, reviews output |

Total capacity is roughly equivalent to 5-6 FTE (full-time equivalent).

### 4.2 RACI per Epic

R = Responsible, A = Accountable, C = Consulted, I = Informed

| Epic | PO | SA | BE | DE | OCR Eng | Integration Eng | Security Eng | QA |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sprint 0 – Discovery | A | R | C | C | C | C | C | I |
| Epic A – Receipt OCR Pipeline | I | A | C | I | R | I | C | C |
| Epic B – Bank File Ingestion | I | A | C | R | I | C | C | C |
| Epic C – Matching Engine | C | A | C | R | I | I | I | C |
| Epic D – Exception & Finance Workflow | A | C | R | I | I | I | I | C |
| Epic E – Notification & Reporting | A | C | C | I | I | R | I | C |
| Epic F – Security, RBAC, Audit (cross-cutting) | I | A | C | C | C | C | R | C |
| UAT & Pilot Go-Live | A | C | C | C | C | C | C | R |

Note: Epic F (security/audit) is not a separate sprint at the end – every other epic must include security sub-tasks (audit logging, input validation, RBAC) from the start, per the “security by design” principle in Section 21 of the earlier document. The Security Engineer is involved in every sprint review as a reviewer, not just showing up in the final sprint.

## 5. Product Backlog (Epic Level)

This backlog is derived directly from the Functional Requirements (FR-001 through FR-020) in the earlier technical design document, grouped into epics with rough story-point estimates (Fibonacci: 1, 2, 3, 5, 8, 13) – these estimates are indicative and must be re-refined by the team in Sprint 0/1 through planning poker.

| Epic | Scope Summary | Related FRs | Point Estimate |
| --- | --- | --- | --- |
| A. Receipt OCR Pipeline | Upload, classification, OCR, field extraction, confidence scoring, teller string generator | FR-001 through FR-007 | 34 |
| B. Bank File Ingestion & Normalization | Folder watcher, readiness check, per-bank XLSX parsing, dedup | FR-008 through FR-011 | 26 |
| C. Matching Engine | Hierarchical matching Levels 1-3, scoring, auto-verify | FR-012 through FR-014 | 29 |
| D. Exception Handling & Finance Workflow | Exception queue, finance decisions, decision audit | FR-015, FR-016 | 18 |
| E. Notification & Reporting | Teams/WA notifications, XLSX export | FR-017, FR-018 | 13 |
| F. Security, RBAC & Audit Logging (cross-cutting) | SSO, RBAC, secrets vault, audit trail | FR-019, FR-020 | 21 (spread across all sprints) |
| Total |  |  | ~141 points |

With a team of ~5-6 FTE and a conservative initial velocity assumption of ~20-25 points/sprint (real velocity can only be confirmed after the first 2 sprints), this backlog can realistically be completed in 6 development sprints (Sprints 1-6), matching the timeline in Section 6.

## 6. Sprint Plan & Timeline

Week:       1-2      3-4      5-6      7-8      9-10     11-12    13-14    15-16
            |--------|--------|--------|--------|--------|--------|--------|--------|
Sprint:     Sprint0  Sprint1  Sprint2  Sprint3  Sprint4  Sprint5  Sprint6  Sprint7
            Discover Found.   Epic A   Epic B   Epic C   Epic D+E Harden.  UAT+Pilot
                     +Epic A          (cont.)                    +Perf    Go-Live

| Sprint | Focus | Output/Demo | Dependency |
| --- | --- | --- | --- |
| Sprint 0 (Weeks 1-2) | Discovery, data access, environment setup (Section 3) | Complete DoR checklist, architecture approved, backlog refined | Security/IT approval for the base architecture |
| Sprint 1 (Weeks 3-4) | Foundational: DB schema, API skeleton, bot transaction API, object storage, CI/CD; start Epic A (upload + rule-based classification) | Demo: customer submits a transaction via the bot -> stored in DB; receipt upload -> stored in storage | Sprint 0 complete |
| Sprint 2 (Weeks 5-6) | Epic A continues: OCR provider integration, field extraction for 2-3 priority banks, confidence scoring, deterministic teller string formatter | End-to-end demo: receipt -> structured fields -> teller string generated automatically | OCR provider trial active |
| Sprint 3 (Weeks 7-8) | Epic B: folder watcher, readiness check, per-bank XLSX parser, normalization, dedup | Demo: an XLSX file is dropped into the folder -> appears in bank_transactions, normalized | Sample bank XLSX available (Sprint 0) |
| Sprint 4 (Weeks 9-10) | Epic C: matching engine Levels 1-3, scoring, a conservative auto-verify threshold | End-to-end demo with sample data: bot transaction + bank data -> a match/score result | Epics A & B complete |
| Sprint 5 (Weeks 11-12) | Epic D + E: exception queue, finance decision workflow, Teams/WA notifications, XLSX export, basic RBAC | Demo: an exception transaction appears in the queue, finance approves/rejects, a notification is sent | Epic C complete |
| Sprint 6 (Weeks 13-14) | Hardening: complete audit logging, full security review, a load test simulating 500 transactions/day, bug fixing | Security review + load test report, bug backlog cleared | All functional epics complete |
| Sprint 7 (Weeks 15-16) | UAT together with finance (shadow-run in parallel with the manual process), fix feedback, deploy to production, pilot go-live with 1-2 banks | UAT sign-off, the system is live for a subset of transactions, hypercare begins | Sprint 6 complete, security sign-off |

Important note: Sprint 7 deliberately uses a shadow-run scheme (the new system runs in parallel, finance keeps the manual process as a fallback) before actually replacing the old process – this is a standard risk mitigation for a system that touches financial reconciliation.

## 7. Ceremony Cadence

| Ceremony | Frequency | Duration | Participants |
| --- | --- | --- | --- |
| Daily Standup | Daily | 15 minutes | The whole delivery team |
| Sprint Planning | Start of each sprint | 2 hours | Delivery team + PO |
| Backlog Refinement | Mid-sprint | 1 hour | Delivery team + PO |
| Sprint Review/Demo | End of each sprint | 1 hour | Delivery team + PO + Finance SME (stakeholder) |
| Sprint Retrospective | End of each sprint | 45 minutes | Delivery team + SM |
| Security Review Checkpoint | Every 2 sprints | 1 hour | Security Engineer + SA + related team members |

## 8. Definition of Done (Example, to Be Re-Agreed in Sprint 0)

A story is considered “Done” when:

- The code has been reviewed by at least 1 other reviewer and passes CI (unit test + lint).

- Unit tests exist for critical logic (formatter, scoring, normalization) – per the deterministic testing principle in Section 27 of the earlier document.

- No credentials/secrets are hardcoded (checked automatically in CI).

- Any change to the data model comes with a migration script.

- Audit logging for the new state transition has been verified to exist.

- It has been demoed at Sprint Review and accepted by the PO.

## 9. Phase 2 & Phase 3 Roadmap (High Level)

Month:        1    2    3    4    5    6    7    8    9   10   11   12
Phase 1 MVP   [====================]
Phase 2                              [========================]
Phase 3                                                        [========>

- Phase 1 (Months 1-4): the MVP per Section 6, pilot with 1-2 banks.

- Phase 2 (Months 5-8): add support for other banks/formats, a full finance dashboard, migration to SharePoint/Graph API (if approved), recalibrating matching thresholds with real production data.

- Phase 3 (Month 9+): evaluate direct bank API/host-to-host integration, ML-assisted prioritization (with a human in the loop still mandatory), high-availability multi-region if scale demands it.

## 10. Risks to the Timeline

| Risk | Impact on Timeline | Mitigation |
| --- | --- | --- |
| Confirmation of the teller string field meanings (3rd/8th) is delayed | Blocks Epic A from Sprint 1 onward | Make it item number one in Sprint 0, escalate to management if there’s no answer after >1 week |
| Security approval for the architecture (folder/cloud) is delayed | Blocks Sprint 1 from starting | Start briefing security from the first week of Sprint 0, don’t wait for the architecture to be 100% final |
| Sample bank/receipt data isn’t representative | Rework in Sprint 2-3 once real cases are encountered | Collect as wide a variety of sample cases as possible in Sprint 0, including “bad” cases (blurry, odd formats) |
| Team velocity comes in below the assumption (~20-25 points/sprint) | The MVP timeline slips past 16 weeks | Re-forecast after the first 2 sprints, communicate to stakeholders early rather than at the end |
| The Finance SME is unavailable for UAT (Sprint 7) | The pilot go-live is delayed | Lock the UAT schedule at the start of the project as a cross-team commitment, not a last-minute negotiation |

## 11. Cost Estimate – 500 Transactions/Day Scenario

Methodology note: all salary figures below are drawn from several 2026 Malaysia tech salary benchmark reports (Seekers.my, Shelby Global ASEAN, and similar) as of September 2026. These are indicative estimates for initial budget planning, not official quotes – the real rate depends on the specific candidate’s seniority, negotiation, and whether they’re hired in-house, on contract, or through a vendor/agency.

### 11.1 Sizing Basis for 500 Transactions/Day

- ~500 receipts/day -> ~15,000/month of OCR volume.

- ~500 customer interactions/day via the WhatsApp bot (mostly within the free 24-hour service window, see Appendix C.3 of the earlier document).

- Compute needs are still in the “small-to-medium” class – a few small VMs/containers are enough, not a large cluster (see Section 32 of the earlier document: 500/day sits between the 100/day and 1,000/day tiers).

### 11.2 Team Cost to Build the MVP (In-House Scenario, 4 Months)

| Role | Allocation | Estimated Monthly Rate (RM) | Duration | Subtotal (RM) |
| --- | --- | --- | --- | --- |
| Solution Architect | 50% | 18,000 (architect/senior band ≈ RM14,000-22,000) | 4 months | 36,000 |
| Backend Engineer x2 | 100% each | 8,000/person (mid-level band ≈ RM5,800-9,500) | 4 months | 64,000 |
| Data Engineer | 75% | 8,500 (median data engineer market rate ≈ RM8,500) | 4 months | 25,500 |
| OCR/Document AI Engineer | 75% | 9,500 (close to the data scientist/ML band) | 4 months | 28,500 |
| Automation/Integration Engineer | 100% | 7,500 (mid-level backend band) | 4 months | 30,000 |
| Security Engineer (part-time/consultant) | 30% | 12,000 (mid-senior cybersecurity band ≈ RM7,000-13,000) | 4 months | 14,400 |
| QA Engineer | 50% | 6,500 | 4 months | 13,000 |
| Product Owner/PM (+Scrum Master) | 50% | 9,000 | 4 months | 18,000 |
| Base salary subtotal |  |  |  | 229,400 |
| Statutory on-costs (EPF ~13%, SOCSO/EIS below the RM6,000 wage ceiling, HRDF ~1%) | ~13-15% |  |  | ≈ 34,400 |
| Total estimated MVP team cost (in-house) |  |  |  | ≈ RM 260,000 – 265,000 |

On-cost reference: employer EPF ≈ 12-13% of salary, SOCSO ≈ 1.75% and EIS ≈ 0.2% of salary (both capped at a RM6,000/month wage ceiling, so the effective percentage against a senior salary is far lower than 1.75%/0.2%), HRDF 1% where applicable.

### 11.3 Alternative Scenario: Outsourcing/Turnkey Vendor

As a comparison, a fully outsourced model (a vendor builds the MVP end-to-end) is typically priced with a blended day rate per person-day, already including the vendor’s margin:

| Model | Estimate | Note |
| --- | --- | --- |
| In-house hire (Section 11.2) | ≈ RM 260,000-265,000 | Requires upfront recruiting time, but the team becomes a long-term company asset |
| Outsourcing/turnkey vendor | ≈ RM 300,000-500,000 | Blended rate of RM800-1,500/person-day x ~5 person-equivalents x ~80 effective working days; faster to start but usually more expensive for a project this size, and product knowledge doesn’t fully stay in-house |
| Hybrid (in-house core team + 1-2 contracted specialists, e.g. OCR/security) | ≈ RM 270,000-320,000 | A common compromise – scarce specialists (OCR, security) are contracted short-term, the core team stays in-house |

### 11.4 Monthly Operational Cost Post-Go-Live (500 Transactions/Day)

Referencing and scaling Appendix C of the earlier document to a volume of 500/day:

| Component | Monthly Estimate | Note |
| --- | --- | --- |
| OCR provider (Read tier + some prebuilt for low-confidence cases) | ≈ USD 100-150 (≈ RM 470-700) | ~15,000 pages/month, blended between the cheapest tier and the prebuilt receipt model |
| WhatsApp BSP platform fee | ≈ RM 300-800 | Depends on the provider (Twilio/360dialog/Qiscus/etc.) |
| WhatsApp business-initiated messages (reminders, etc.) | ≈ RM 50-150 | Assumes only a small share of transactions need a reminder outside the service window |
| Compute (small-to-medium VM/container, 2-3 instances) | ≈ USD 150-300 (≈ RM 700-1,400) | Backend + worker + file watcher |
| Managed database (small instance) | ≈ USD 50-100 (≈ RM 230-470) | Can be combined with the compute above if using your own VM for the DB |
| Object storage (receipts + XLSX archive) | ≈ USD 10-30 (≈ RM 50-140) | Volume is still small at this stage |
| Microsoft Entra ID P1 (if not already covered by an existing M365 license) | ≈ USD 50-70 (≈ RM 230-330) for ~8 internal users | Check first – often already included in the M365 E3/E5 bundle |
| Monitoring | ≈ RM 0-200 | Self-hosted (Prometheus/Grafana) is nearly free beyond the compute already counted |
| Total estimated monthly opex | ≈ RM 1,800 – 3,800/month | Excluding post-go-live maintenance/support team costs |

### 11.5 Estimated Total Year 1 Cost

Assuming pilot go-live at the end of month 4, so Year 1 = 4 months of build + 8 months of operations:

| Scenario | Build Cost (4 months) | Operational Cost (8 months x RM1,800-3,800) | Total Year 1 |
| --- | --- | --- | --- |
| In-house | RM 260,000-265,000 | RM 14,400-30,400 | ≈ RM 275,000 – 295,000 |
| Outsourcing/vendor | RM 300,000-500,000 | RM 14,400-30,400 | ≈ RM 315,000 – 530,000 |
| Hybrid | RM 270,000-320,000 | RM 14,400-30,400 | ≈ RM 285,000 – 350,000 |

This does not include the long-term post-hypercare maintenance/support team cost (typically 1-2 part-time people for bug fixes & minor enhancements, outside this document’s scope), and does not include Microsoft licensing the company may already own (don’t double-count).

### 11.6 Sensitivity to Volume

Since the costing basis above uses 500 transactions/day, here is the direction of change for a different volume (see also Section 32 of the earlier document):

- Rising to ~1,000/day: OCR & compute costs rise proportionally but not linearly (still within the same VM tier, may need 1 additional instance) – opex is expected to rise ~30-50%, not 2x.

- Dropping to ~100-200/day: opex can be pushed toward the lower end of the range above, and some OCR volume might even fall within the provider’s free tier.

- The build team cost (Section 11.2) is relatively unaffected by daily volume – it’s a function of feature complexity, not production transaction volume.

## Appendix – Additional Assumptions & Clarifying Questions

- Does the company prefer an in-house hire, outsourcing, or a hybrid model to build this MVP?

- Can the existing internal team (if any) be partially allocated to this project, or does everything need new recruitment/contracting?

- What budget has already been allocated for the build vs. run phases – does RM 275,000-295,000 (the in-house Year-1 scenario) align with expectations?

- Is 500 transactions/day the current figure, or a target projection once the system is live (this affects when infra sizing needs to scale)?

- Who will act as the business-side Product Owner, and what percentage of their time can be allocated?

- Is there a target go-live date already communicated to other parties (regulator, bank partner, etc.) that needs to be treated as a hard constraint against this 16-week timeline?