# Solo Delivery Plan: Payment Verification & Reconciliation Automation

A Plan for One Person to Execute, Setting Up From Scratch

Table of Contents

1. Summary of Approach	1

2. Key Differences vs. the Team Plan	2

3. Phase 0: Setup From Scratch	2

4. MVP-Solo Scope (Trimmed From the Team MVP)	3

5. Solo Backlog (Trimmed, With Point Estimates)	4

6. Solo Timeline (Milestone-Based)	4

7. Day-to-Day Working Rhythm (Replacing Team Ceremonies)	5

8. Definition of Done (Solo-Adjusted)	6

9. When External Help Is Still Needed (Even When Solo)	6

10. Risks Specific to Solo Work & Mitigations	7

11. Cost Estimate – Solo Scenario (500 Transactions/Day as the Target Volume)	8

Appendix – Quick Setup Checklist (Fast Reference)	9

Appendix – Additional Clarifying Questions	10

Version: 1.0 (Adapted from the team Agile Delivery Plan – a companion to the two earlier documents) Methodology: Solo Agile / Personal Kanban, 2-week cycles

## 1. Summary of Approach

The earlier document (the Agile Delivery Plan) assumed a team of ~5-6 FTE. This document is a full adaptation for 1 person handling every role (architecture, backend, data, OCR, automation, integration, and basic security) alone, starting from absolutely nothing (no cloud account, no repo, no environment of any kind yet).

Three fundamental adjustments compared to the team plan:

- The MVP scope is trimmed more aggressively (Section 4) – not 2-3 banks at once like the team plan, but 1 bank first, with non-essential features deferred to Phase 2.

- The timeline is much longer – not because there’s more work, but because there’s no parallelization across specializations. Realistic estimate: ~7 months (not ~4 months like the team plan) to reach pilot go-live.

- Scrum ceremonies are simplified into solo rituals (Section 7) – there’s no point in a daily standup with yourself, but the discipline of planning/review/retro is kept in a lighter form.

One thing that does not change: the technical design principles (deterministic matching, security by design, the database as the source of truth) from the two earlier documents remain fully in force – being solo is not a reason to sacrifice architectural quality, only the delivery speed adjusts.

## 2. Key Differences vs. the Team Plan

| Aspect | Team Plan (earlier document) | Solo Plan (this document) |
| --- | --- | --- |
| Number of people | ~5-6 FTE | 1 person |
| MVP duration | ~16 weeks (~4 months) | ~29 weeks (~7 months) |
| Bank coverage at MVP | 2-3 banks | 1 bank first, the 2nd bank follows in a separate milestone |
| Code review | Peer review between engineers | Rigorous automated testing + periodic external review (Section 8) |
| Security | A Security Engineer involved every sprint | A solo developer + a mandatory external security review before go-live (Section 9) |
| Ceremonies | Daily standup, planning, review, retro | A light daily self check-in, a weekly review (Section 7) |
| Main risk | Coordination across specializations | Single point of failure, expertise blind spots, burnout (Section 10) |

## 3. Phase 0: Setup From Scratch

This is a literal, step-by-step process starting from a truly empty state. Estimated total time: 2-3 calendar weeks (not 2-3 weeks of full-time work – some of it is waiting on external processes such as WhatsApp Business verification, so it can be done in parallel with other steps).

### 3.1 Accounts & Subscriptions (Day 1-2)

- Create a version-control account (GitHub/GitLab) – free for a small private repo.

- Create an account with your chosen cloud provider (Azure/GCP/AWS) – start with a free trial/tier, don’t commit to a paid plan right away.

- Create a trial account with an OCR provider (Azure AI Document Intelligence or Google Document AI) – instant, no approval needed.

- Start the Meta Business Verification process for the WhatsApp Business API – this has an external lead time (can be 3 days to several weeks), so do this on day one, don’t put it off until you actually need it.

- If you’re using a BSP (Twilio/360dialog/etc.) for WhatsApp, sign up for a BSP trial account at the same time.

### 3.2 Local Environment (Day 1-3)

- Install Docker, Python 3.11+, Git, and an IDE (VS Code recommended).

- A basic docker compose setup for local PostgreSQL + Redis.

- Set up the repo with the folder structure from Section 24 of the earlier technical design document.

- Set up basic CI (GitHub Actions free tier for public/small private repos) – lint + unit tests on every push; this is a substitute for the code review a solo developer doesn’t have (see Section 8).

### 3.3 Gather Data & Confirmations (Day 1-10, in parallel with the above)

- Ask finance/tellers for: at least 15-20 sample receipts and 1-2 bank XLSX files (dummy/anonymized) for just 1 priority bank to start.

- Send clarifying questions about the teller string fields (Appendix A/B of the technical design document) to the finance team – a critical blocker, send it on day one, don’t wait until coding starts.

- Confirm that the secure folder (network share) is already accessible for testing the file watcher.

### 3.4 Solo Work-Management Tooling (Day 1)

- Set up a personal kanban board (GitHub Projects, Trello, or Notion – pick whichever is lightest to use solo, don’t over-engineer project-management tooling for 1 person).

- Create a single technical journal file (DECISIONS.md or equivalent) to record architecture decisions and the reasoning behind them – this substitutes for the “team discussion” that would normally produce this documentation naturally.

### 3.5 Definition of Ready to Start Milestone 1

Before starting to code features (not just setup), make sure:

- The local environment works (docker compose up succeeds).

- The CI pipeline is green for an empty/skeleton commit.

- Sample data (receipts + XLSX) for 1 bank is in hand.

- The answer about the teller string fields has been obtained (or a temporary decision has been made with the assumption explicitly recorded, while awaiting final confirmation).

- The WhatsApp Business verification process is already underway (it doesn’t have to be finished, but it must have started).

## 4. MVP-Solo Scope (Trimmed From the Team MVP)

The MVP for a solo developer is deliberately smaller than the team MVP in the earlier document, so there’s a demonstrable result sooner and risk stays controlled. Principle: a thin vertical slice first, expand later.

| Item | Team MVP (earlier document) | MVP-Solo (this document) |
| --- | --- | --- |
| Number of banks | 2-3 banks | 1 bank in the first release, the 2nd bank in a later, separate milestone |
| Matching level | Levels 1-4 (including fuzzy) | Levels 1-3 first, fuzzy matching (Level 4) deferred to Phase 2 |
| RBAC | 4 roles (Reviewer/Admin/Auditor/System) | 2 roles first (Admin, Finance-Viewer), other roles added later |
| Notification | Teams + Excel export | One channel first (choose Teams or email, not both at once) |
| Dashboard | Query/export | Still query/export (same as the team) – a full dashboard UI remains Phase 2+ |
| Security | A security review every sprint | 1 mandatory external security review before go-live (non-negotiable even at a small scope, see Section 9) |

This does not mean quality is sacrificed – the principles of deterministic matching, audit logging, and secrets management from the technical design document remain mandatory from the first release. What’s trimmed is breadth (bank/feature coverage), not depth (the quality & security of each feature that is built).

## 5. Solo Backlog (Trimmed, With Point Estimates)

| Epic | Solo-Trimmed Scope | Point Estimate (Solo) |
| --- | --- | --- |
| A. Receipt OCR Pipeline (1 bank) | Rule-based classification + OCR provider + extraction + confidence + teller string generator | 26 |
| B. Bank File Ingestion (1 bank, then +1 bank) | Folder watcher, readiness check, parser, normalization, dedup | 20 |
| C. Matching Engine (Level 1-3) | Scoring, a conservative auto-verify threshold | 22 |
| D. Exception Handling (simple) | A basic queue, finance decisions via export/DB, no complex UI | 14 |
| E. Notification (1 channel) | Teams or email integration | 9 |
| F. Basic security | Secrets vault, 2-role RBAC, audit log, no full SSO/Conditional Access yet | 16 |
| Total |  | ~107 points |

Assuming a realistic solo velocity of ~9 points/sprint (2 weeks) after a ramp-up period (the first sprint is usually slower, ~6-7 points, from getting used to the OCR API and new tooling):

107 points ÷ ~9 points/sprint ≈ 12-13 development sprints (24-26 weeks), plus Phase 0 (2-3 weeks) = a total of ~27-29 weeks (~6.5-7 months).

## 6. Solo Timeline (Milestone-Based)

Week:      1-3      4-5      6-9      10-13    14-17    18-21    22-25    26-29
           |--------|--------|--------|--------|--------|--------|--------|--------|
Phase:     Phase 0  M1       M2       M3       M4       M5       M6       M7
           Setup    Walking  Real     Bank     Matching Exception Security UAT+
                    Skeleton OCR      Ingest   Engine   +Notif   +Harden  Pilot

| Milestone | Week | Focus | Output |
| --- | --- | --- | --- |
| Phase 0 | 1-3 | Setup from scratch (Section 3) | Environment ready, sample data available, WhatsApp verification underway |
| M1 – Walking Skeleton | 4-5 | A rough end-to-end path: manual input (no real OCR yet) -> teller string generator -> stored in DB; the folder watcher reads 1 dummy file | The simplest possible end-to-end demo, proving the data flow connects from end to end |
| M2 – Real OCR | 6-9 | Integrate a real OCR provider for 1 bank, classification, extraction, confidence scoring, replacing the manual input from M1 | Demo: a real receipt photo -> structured fields -> teller string generated automatically |
| M3 – Real Bank Ingestion | 10-13 | A production folder watcher, readiness check, parser + normalizer for 1 bank (then add a 2nd bank at the end of this milestone) | Demo: an XLSX file is dropped -> normalized data in the DB, for 2 banks |
| M4 – Matching Engine | 14-17 | Levels 1-3 matching + scoring, connecting the outputs of M2 and M3 | Full end-to-end demo: receipt + bank data -> a match/score result |
| M5 – Exception & Notification | 18-21 | A simple exception queue, 1 notification channel, 2-role RBAC, XLSX export | Demo: an exception transaction -> notification -> a recorded decision |
| M6 – Security & Hardening | 22-25 | Secrets vault, complete audit log, a load test at the target volume, external security review (Section 9), bug fixing | Security review report, load test results, bug backlog cleared |
| M7 – UAT & Pilot Go-Live | 26-29 | Shadow-run with finance, fix feedback, deploy to production, pilot go-live with 1 bank, hypercare begins | UAT sign-off, the system is live for a subset of transactions |

## 7. Day-to-Day Working Rhythm (Replacing Team Ceremonies)

Standard Scrum ceremonies are designed for coordination between people – for solo work, most of them are replaced with personal discipline, rather than simply dropped:

| Team Ceremony | Solo Adaptation | Frequency |
| --- | --- | --- |
| Daily Standup | A brief self check-in: what was done yesterday, what’s planned today, any blockers – recorded as 2-3 lines in a work journal | Daily, 5 minutes |
| Sprint Planning | Pick backlog items for the next 2 weeks, estimate points | Start of each milestone/sprint, 30 minutes |
| Backlog Refinement | Re-review priorities, break large tasks into smaller ones | Weekly, 20 minutes |
| Sprint Review/Demo | Demo to yourself (record a short screen recording) + if possible, show it to 1 PO/finance representative as an external stakeholder | End of each sprint, 15-30 minutes |
| Sprint Retrospective | Write 3 lines in the journal: what went well, what didn’t, what to change next sprint | End of each sprint, 10 minutes |

Why these rituals are kept even when working alone: without explicit checkpoints, a solo developer is highly prone to silent scope creep (adding features “while I’m at it” without realizing it) and losing track of why a decision was made. This brief journaling is cheap but has an outsized effect on maintaining focus and leaving a trail for your future self 3 months from now (or for someone else, if this project is ever handed over).

## 8. Definition of Done (Solo-Adjusted)

Since there’s no colleague for manual code review, several items below substitute for the function of human review:

- Code passes automated CI: lint + unit test + (ideally) basic security static analysis (e.g. bandit for Python) – this substitutes for the “second pair of eyes” that would normally come from peer review.

- Critical logic (the teller string formatter, the scoring engine, normalization) must have unit tests, not optionally – because there is no other reviewer who will catch a logic bug here before production.

- No credentials/secrets are hardcoded (checked automatically in CI, same as the team plan).

- Every non-trivial architecture decision is recorded in DECISIONS.md (Section 3.4) – a substitute for the design discussion that normally happens naturally within a team.

- Occasionally (ideally every 4-6 weeks), ask for a brief external review from another developer (a colleague, a mentor, or a contractor paid for a few hours) to read part of the code – a solo developer has blind spots that will never be visible to themselves.

## 9. When External Help Is Still Needed (Even When Solo)

Solo doesn’t mean truly alone with no help whatsoever – the following points must not be handled solo without outside input, no matter how competent the developer is:

| Need | Why It Can’t Be Fully Solo | Form of Help |
| --- | --- | --- |
| Confirming the teller string fields & business requirements | The developer has no authority to define the business meaning of an internal finance field | Written input from the finance/teller team (Section 3.3) |
| Security review/penetration test before go-live | Self-reviewing security as the same person who wrote the code has an inherent blind spot; this system touches customers’ financial data | Contract an external security review – a micro/small-scale assessment in Malaysia typically runs RM 5,000-15,000 for 1-2 applications/a small scope. Compliance note: since the Cyber Security Act 2024, penetration testing is a licensed activity in Malaysia (regulated by NACSA) – make sure the provider used is properly licensed |
| Architecture & folder/network access approval | Company infrastructure security decisions are not within 1 developer’s authority | Sign-off from the IT/security team (still needed even if the delivery team is just 1 person) |
| UAT (User Acceptance Test) | The developer cannot test “does this make sense for finance” from their own point of view | A UAT session with real finance/teller staff (Milestone 7) |
| Knowledge backup (“bus factor”) | If the developer gets sick/takes leave/leaves, the project must not stop entirely | Ideally there is 1 other person (internal or a contractor) who knows the system’s broad strokes, even without being full-time involved – documentation in DECISIONS.md (Section 3.4) is key here |

## 10. Risks Specific to Solo Work & Mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Single point of failure (illness, leave, resignation) | The project stops completely without warning | Continuous decision documentation (DECISIONS.md), code kept as simple as possible (avoid cleverness that only the author understands) |
| No peer review | Logic or security bugs slip through undetected | Rigorous automated testing + periodic external review (Section 8) |
| Expertise blind spots (security, OCR/ML aren’t the main specialty) | Suboptimal technical decisions in less-mastered areas | Budget explicit learning time in M2 and M6 (Section 6), plus a mandatory external security review (Section 9) |
| Scope creep with no gatekeeper (no PO pushing back) | The timeline slips without anyone noticing | Backlog discipline + a WIP limit on the personal kanban board (Section 3.4), an honest weekly retro (Section 7) |
| Burnout (covering many roles at once) | Quality drops, and the timeline actually slips further | This 7-month timeline is already designed to be realistic (not compressed) – don’t be tempted to speed it up with sustained overtime, that only increases the risk of bugs & burnout |
| Dependency on external processes (WhatsApp verification, security approval, finance sample data) | Can become a bottleneck outside the developer’s control | Start all these external processes on Phase 0, day one, don’t wait until “it’s time” – this is why Phase 0 in Section 3 emphasizes this |

## 11. Cost Estimate – Solo Scenario (500 Transactions/Day as the Target Volume)

Same methodology as the earlier documents: salary figures are drawn from 2026 market benchmarks (ERI SalaryExpert, Seekers.my) as of September 2026 – indicative for planning, not an official quote.

### 11.1 “Team” (1 Person) Cost to Build the MVP-Solo (~7 Months)

| Scenario | Rate | Calculation | Total |
| --- | --- | --- | --- |
| In-house (existing staff reassigned full-time / a new hire) | RM 12,000-16,000/month (Malaysia senior full-stack generalist band; the senior full-stack market average ≈ RM14,690/month per ERI SalaryExpert data) | x 7 months | RM 84,000-112,000 |
| Statutory on-costs (EPF ~13%, SOCSO/EIS capped, HRDF ~1%) | ~14% |  | ≈ RM 12,000-16,000 |
| In-house subtotal |  |  | ≈ RM 96,000 – 128,000 |
| Alternative: independent contractor/freelancer | RM 800-1,200/day | x ~140 working days (7 months x 20 days) | ≈ RM 112,000 – 168,000 (all-in, with no additional on-cost since they’re not an employee) |

### 11.2 Mandatory External Costs (Cannot Be Skipped Even When Solo)

| Item | Estimate | When |
| --- | --- | --- |
| Security review/penetration test (small scope, 1 application) | RM 5,000-15,000 | Before pilot go-live (Milestone 6) |
| Periodic external code review (optional but recommended, a few hours/month) | RM 1,000-3,000/month if used | Throughout the project, optional |

### 11.3 Monthly Operational Cost Post-Go-Live (500 Transactions/Day)

Same as Appendix C of the technical design document and Section 11.4 of the team’s Agile Delivery Plan – customer transaction volume doesn’t shrink just because the delivery team is solo, so infrastructure cost at full scale stays the same:

| Component | Monthly Estimate |
| --- | --- |
| OCR provider | ≈ USD 100-150 (≈ RM 470-700) |
| WhatsApp BSP + messages | ≈ RM 350-950 |
| Compute + DB + storage | ≈ USD 210-430 (≈ RM 980-2,010) |
| Microsoft Entra ID (if not already covered by an existing license) | ≈ RM 230-330 |
| Total monthly opex (at full scale) | ≈ RM 2,000 – 4,000/month |

Note: while the MVP-Solo only covers 1 bank (Milestones 1-6), the real transaction volume the system processes is likely smaller than 500/day (depending on how large a share of customers use that bank) – actual opex during this period is likely at the lower end of the range, rising to the full estimate after rollout to the 2nd bank and full volume is reached.

### 11.4 Estimated Total Year 1 (Solo Scenario)

Assuming pilot go-live at the end of month 7, so Year 1 = 7 months of build + 5 months of operations:

| Scenario | Build (7 months) + Security Review | Operations (5 months x RM2,000-4,000) | Total Year 1 |
| --- | --- | --- | --- |
| In-house | RM 96,000-128,000 + RM 5,000-15,000 = RM 101,000-143,000 | RM 10,000-20,000 | ≈ RM 111,000 – 163,000 |
| Contractor/freelancer | RM 112,000-168,000 + RM 5,000-15,000 = RM 117,000-183,000 | RM 10,000-20,000 | ≈ RM 127,000 – 203,000 |

### 11.5 Brief Comparison With the Team Plan

|  | Team Plan (earlier document) | Solo Plan (this document) |
| --- | --- | --- |
| Total Year 1 (in-house) | ≈ RM 275,000-295,000 | ≈ RM 111,000-163,000 |
| Time to pilot go-live | ~4 months | ~7 months |
| Bank coverage at go-live | 2-3 banks | 1 bank |

Solo is cheaper in direct cost, but takes longer and carries a concentration risk (Section 10) that doesn’t exist in the team model. This is a trade-off that decision-makers need to be explicitly aware of, not simply “solo = cheaper.”

## Appendix – Quick Setup Checklist (Fast Reference)

- ☐ GitHub/GitLab account

- ☐ Cloud provider account (trial/free tier)

- ☐ OCR provider trial account

- ☐ Start Meta Business Verification for the WhatsApp Business API

- ☐ Docker, Python, Git, IDE installed locally

- ☐ docker compose PostgreSQL + Redis running locally

- ☐ Repo + folder structure + basic CI (lint + test)

- ☐ Sample receipts (15-20) for 1 priority bank

- ☐ Sample bank XLSX (1-2 files) for the same bank

- ☐ Written confirmation of the meaning of teller string fields 3/8 from finance

- ☐ Secure folder access (network share) for the file watcher

- ☐ Personal kanban board created

- ☐ DECISIONS.md file created

## Appendix – Additional Clarifying Questions

- Is the person doing this work an internal staff member reassigned full-time, or does someone need to be recruited/contracted externally?

- Does this person already have prior exposure to OCR/Document AI, or will this be a new area to learn (affecting whether the ~7-month estimate is realistic or needs additional buffer)?

- Who will act as the “second person” for periodic external review and as a minimum knowledge backup (Section 9)?

- Can the budget for the external security review (RM 5,000-15,000) be allocated from the start of the project, rather than later “if there’s time”?

- Which bank is the top priority for MVP-Solo (Milestones 1-3)?